## Slide 1: Precious Metals and Rhenium Consortium PGM Experts meeting
Conference Call
8th May 2012

## Slide 2: 1. Introduction and welcome
  Competition Law reminder
  Approval of the Agenda
  Approval of minutes last meeting
  US EPA 8(e) reporting requirements

## Slide 3: 2. PGM Testing Programme

## Slide 4: Enabling- /phys.-chem. Tests – progress update

## Slide 5: Oxidising Properties – tests at BAM
Substance | CAS | State | Status
Iridium dioxide | 12030-49-8 | solid | done
Platinum dioxide | 1314-15-4 | solid | done
Platinum dinitrate | 18496-40-7 | solution | done
Dipotassium tetraoxoruthenate | 31111-21-4 | Solution in aqueous KOH | Not available in pure form test K2OsO4 instead, done
Ruthenium IV oxide | 12036-10-1 | solid | done
Rhodium trinitrate | 10139-58-9 | Solid (hydrate) | done
Dihydrogen hexahydroxyplatinate | 51850-20-5 | Solid | New test - ongoing
Initial tests completed at BAM, Berlin
Agreed to confirm ox. prop. of dihydrogen hexahydroxyplatinate
  Testing ongoing at BAM
  Currently Cat. 1 based on read across
  Results in May

## Slide 6: Water Solubility –Standard tests
OECD 105 (shake flask test)
Tests at JMTC completed
1 result from external lab outstanding
  expected in June
10025-65-7 Platinum dichloride
Dicarbonyl(pentane-2,4-dionato-O,O')rhodium 14874-82-9
Triammonium hexachlororhodate 15336-18-2
Diammonium sodium hexakis(nitrito-N)rhodate 64164-17-6
Diammonium hexachlororuthenate 18746-63-9
Tetraammonium decachloro-mu-oxodiruthenate(4-) 85392-65-0
Rhodium trichloride (anhydrous) 10049-07-7
Ruthenium trichloride 10049-08-8 (anhydrous)
Iridium dioxide 12030-49-8

## Slide 7: Water Solubility – Non standard tests
Substance | Comment
Rhodium trihydroxide 21656-02-0 | cannot be isolated as dry solid
Rhodium tris(2-ethylhexanoate) 20845-92-5 | solution in 2-EH
Ruthenium trihydroxide 12135-42-1 | damp unisolated solid
16970-55-1 Dihydrogen tetrachloropalladate | only available as solution
68478-92-2 Platinum, 1,3-diethenyl-1,1,3,3-tetramethyldisiloxane complexes / Karstedt concentrate (10-100 tonne substance) | decomposes in water
14221-01-3 Tetrakis(triphenylphosphine)palladium | decomposes in water
10102-05-3 Palladium dinitrate (and solution) | likely to precipitate in water
18496-40-7 Platinum dinitrate | likely to precipitate in water
12036-04-3 Palladium dioxide (and hydrate) | substance not isolated
16919-73-6 Dipotassium hexachloropalladate | substance not isolated
19168-23-1 Diammonium hexachloropalladate | substance not isolated
Testing at JMTC
2 results outstanding
  1 substance received late (3rd May 2012)
  Karstedt conc. put on hold – recommend to test now

## Slide 8: Water Solubility – TD - Other
Substance | Status
Palladium monoxide (hydrate) 1314-08-5 | TD test CANMET
Palladium dihydroxide 12135-22-7 | TD test CANMET
14024-61-4 Palladium di(4-oxopent-2-en-2-oate) | Existing data sufficient, no TD test required
Dirhodium trisulphate 10489-46-0 | Check if limit value available - done
Potassium tetraoxoruthenate 31111-21-4 | Check if limit value available - done
61495-96-3 Tetramminepalladium(2+) diacetate (1-10 tonne substance) | Check if limit value available - done
Testing at CANMET completed
Draft report received
Final report in preparation

## Slide 9: Bio-elution tests
Testing at CIMM, Chile
Timing: CIMM will close down – need to complete testing by summer
Final scope based on initial data from dustiness tests/ MPPD modeling (next slides)
PdO: no sample provider found
Substance | CASRN | Comment | Gastric/ Dermal | Lung
Platinum | 2023600 |  | x | 
Platinum black |  |  | x | x
Palladium | 7440-05-3 |  | x | 
Palladium black |  |  | x | x
Palladium monoxide (anhydr.) | 1314-08-5 | Substance not available for testing | x | 
Palladium dihydroxide | 12135-22-7 |  | x | 
Palladium (II) di(4-oxopent-2-en-2-oate) | 14024-61-4 |  | x | 
Rhodium | 7440-16-6 |  | x | 
Rhodium black |  |  | x | x
Diammonium sodium hexakis(nitrito-N)rhodate | 64164-17-6 |  | x | 
Ruthenium | 7440-18-8 |  | x | 
Ruthenium black |  |  | x | x

## Slide 10: Dustiness tests
To estimate potential for inhalation exposure
Status
  Testing at DMT completed, reports available
  Lung deposition modelling (MPPD) based on dustiness data: completed, draft report received 30th April 2012
  Draft results: next slide
Breathing mode for MPPD calculations
  Several modes available (oro-nasal augmenter, oro-nasal mouth, mouth)
  Need to select ‘reasonable worst-case’ mode. Suggest to use oro-nasal augmenter
  Any objections?
Selection of substances for bio-elution testing in lung fluids
  Only needed if substance reaches the lung
  Selection based on draft MPPD data and dustiness
  Recommendation: test lung fluids bio-elution only for substances with lung deposition > 1%

## Slide 11: Dustiness tests/ MPPD modeling - Draft results
Substance name | Oronasal-augmenter |  |  |  | Dustiness
 | Head (%) | TB (%) | P (%) | Total (%) | %
Diamminedichloropalladium | 52.2 | 0.29 | 0.44 | 52.9 | 22
Dihydrogen hexahydroxyplatinate | 66.4 | 1.1 | 2.4 | 69.9 | 26.2
Palladium dihydroxide | 46.6 | 0.16 | 0.19 | 47.0 | 13.9
Diammonium sodium hexakis(nitrito-N)rhodate | 47.7 | 0.20 | 0.32 | 48.2 | 23.7
Diammonium hexachloropalladate | 48.0 | 0.11 | 0.062 | 48.1 | 43.5
Dipotassium hexachloropalladate | 52.5 | 0.17 | 0.15 | 52.8 | 55.8
Tetraamminepalladium(2+)dichloride | 52.5 | 0.17 | 0.15 | 52.8 | 1
Diammonium hexachlororuthenate | 47.6 | 0.18 | 0.26 | 48.1 | 34.1
Palladium di(4-oxopent-2-en-2-oate) | 40.0 | 0.14 | 0.26 | 40.4 | 23.2
Ruthenium black* | 53.2 | 0.60 | 0.81 | 54.6 | 40.1
Palladium black* | 79.6 | 0.76 | 0.79 | 81.1 | X
Platinum black* | 72.3 | 1.8 | 6.0 | 80.1 | 20.5
Rhodium black* | 48.7 | 0.20 | 0.28 | 49.2 | 51.5
Palladium monoxide (anhydrous)* | 46.3 | 0.12 | 0.085 | 46.5 | 56.7
Platinum sponge* | 43.9 | 0.098 | 0.053 | 44.1 | 7.3
Rhodium sponge* | 50.4 | 0.18 | 0.18 | 50.8 | 26.3
Palladium powder* | 45.8 | 0.12 | 0.08 | 46.0 | 28.4
Ruthenium powder* | 54.9 | 0.69 | 0.89 | 56.4 | 4.9

## Slide 12: In-vitro irritation/corrosion testing
Testing strategy
  In-vitro skin irritation (OECD 439) – if positive: OECD 431
  In-vitro skin corrosion (OECD 431) – if positive: stop
  In-vitro eye irritation (ICE or BCOP) – if positive: stop
  In-vivo eye irritation
Skin corrosion data needed to decide on other tests
  Eye irritation
  Sensitisation
  Acute toxicity
  (Genotoxicity)

## Slide 13: Irritation/corrosion testing
Testing ongoing
  CiToxLAB (EPISKIN/ ICE): in vitro tests completed, in-vivo tests ongoing
  Harlan (EPISKIN/ BCOP): substance not available yet
Substance | In vitro skin (EPISKIN) test | In vitro eye (e.g. BCOP or ICE) test | In vivo eye irritation test | 
Diammonium hexachlororuthenate (CAS 18746-63-9) | Not irr./corr. | ICE neg | ongoing | Initial in-vivo data indicate possible irritation, need to confirm with water solubility data (in progress)
Carbonyl(pentane-2,4-dionato-O,O')(triphenylphosphine)rhodium (CAS 25470-96-6) |  | - | - | Due to reduction in tonnage, substance now qualifies for Annex III exemption. No testing required any longer.
Diammonium sodium hexakis(nitrito-N)rhodate (CAS 64164-17-6) | Not irr./corr. | ICE neg. | neg. | ICE
Diamminedichloropalladium (CAS 13782-33-7) | Not irr./corr. | ICE neg. | Cat 1 | ICE
Palladium (II) di(4-oxopent-2-en-2-oate) (CAS 14024-61-4) | Not irr./corr. | neg. | Cat 1 | N/A
Platinum dichloride (CAS 10025-65-7) |  |  |  | Out of scope now
Tetraammineplatinum dinitrate (CAS 20634-12-2) | Not irr./corr. | Substance not available yet | Substance not available yet | Supplied as solution, max. conc. 6.6%. Makeup of 20% solution from solid is not possible since solid is not isolated (explosivity); suggest to test 6.6% solution in BCOP test.
Platinum, 1,3-diethenyl-1,1,3,3-tetramethyldisiloxane complexes / Karstedt concentrate (CAS 68478-92-2) | (X) | (X) | (X) | Data sharing under discussion with Silicones sector. Suggest to put testing on hold. (Will decompose in aqueous solution. Consider waiver possibility. Predicted to be a marked irritant.)
Dihydrogen hexahydroxyplatinate (CAS 51850-20-5) | Not irr./corr. |  |  | 

## Slide 14: Fast-track testing: diamminedichloropalladium

## Slide 15
DIAMMINEDICHLOROPALLADIUM: ECOTOXICOLOGY STUDIES |  |  | 
Study | CRO | Status | Comments
ALGAE (OECD 201) | Fraunhofer | Completed | Fraunhofer, recommended to PMRC 13.12.2011, confirmation required from PEG WG to proceed. Confrmation received 28/12/2011. Confirmed test scope with Fraunhofer 16/1/2012: - low EDTA media, - water quality parameters to inc. DOC & to be measured in RF & definitive tests. Revised quote/contract from Fraunhofer received 25/1/2012. Based on the results of range-finder the definitve test will be performed at nominal test concentrations of 10.0, 5.0, 2.5, 1.25, 0.625 µg Pd/L. Draft report received 25/3/2012. Exposure concentrations (based on Pd analysis) were at 26-62% of nominal at the start of the test and dropped to 14-21% of nominal after 72 hours. Toxicity results are therefore based on geometric mean measured exposure concentrations. Based on the geometric mean measured Pd concentrations; EC50 Yield = 2.03 mg/L Pd/ 4.03 mg/L DDP EC50 Growth Rate = 2.96 mg/L Pd/ 5.88 mg/L DDP NOEC Growth Rate & Yield = 1.33 mg/L Pd/ 2.64 mg/L DDP
DAPHNIA (OECD 202) | Fraunhofer | Reporting | Fraunhofer, recommended to PMRC 13.12.2011, confirmation required from PEG WG to proceed. Confrmation received 28/12/2011. Confirmed test scope with Fraunhofer 16/1/2012: - low EDTA media, - water quality parameters to inc. DOC & to be measured in RF & definitive tests. Revised quote/contract from Fraunhofer received 25/1/2012. Based on the results of the range-finding test, the definitive test will be undertaken at nominal test concentrations of 100, 50, 25, 12.5 and 6.25 µg Pd/L. Initial definitive test completed without filtration of analytical samples. Test requires repeat (no extra cost).
FISH (OECD 203) | Fraunhofer | In progress | Fraunhofer, recommended to PMRC 13.12.2011, confirmation required from PEG WG to proceed. Confrmation received 28/12/2011. Decision required on static v semi-static. Confirmed test scope with Fraunhofer 16/1/2012: - static RF with analysis at lowest & highest exposure conc. - decision on regime in def. test will depend on RF results, - water quality parameters to inc. DOC & to be measured in RF & definitive tests). Revised quote/contract from Fraunhofer received 25/1/2012. Based on the results of range-finder (static) the definitive test will be performed at nominal test concentrations of 1000, 500, 250, 125 and 62.5 µg Pd/L. Analytical results of the range-finder tests received 15/2/2012. These indicate instability of the test compound over the duration of the test and therefore the definitive test will be conducted under semi-static exposure conditions. In life phase completed; currently discussing analytical results with lab
ASRIT (OECD 209) | LAUS (sub-contracted by Fraunhofer) | Completed | Fraunhofer, recommended to PMRC 13.12.2011, confirmation required from PEG WG to proceed. Confrmation received 28/12/2011. Confirmed test scope with Fraunhofer 16/1/2012: Fraunhofer reported that they cannot achieve ASRIT validity criteria or provide sufficient test replication & therefore have been asked to identify a sub-contractor to undertake this test. Fraunhofer identified LAUS as suitable sub-contractor able to achieve validity criteria and required level of replication. Fraunhofer will manage sub-sampling of test item for use by LAUS. Prelminiary test indicated that a definitve test will be required. Draft report available 19/3/2012; EC50 = 61 mg/L DDP NOEC = 18 mg/L DDP Final report submitted 22/3/2012.

## Slide 16
DIAMMINEDICHLOROPALLADIUM: TOXICOLOGY STUDIES |  |  |  |  |  | 
Study | CRO | Availability of results | Proposed draft report date | Final Report Issued | Status | Comments
Episkin OECD TG431 | LAB |  |  |  |  | Not required as OECD 439 indicates not irritating. Study cancelled 2 Mar 12.
Episkin OECD TG439 | LAB | 14. Feb 12 | 24. Feb 12 |  | Comments returned to Lab | Non irritant
in vitro eye irritation (ICE) | LAB | w/c 5-Mar | 23. Mrz 12 |  | Comments returned to Lab | Non irritant
in vivo eye irritation OECD TG405 | LAB | 16. Apr 12 | 25. Mai 12 |  | In live complete | 3 animals , 21 days observation
Sensitisation OECD TG429 (LLNA) | HARLAN | 3 months from study commencement | Jun 12 |  | Study complete?? (asked for results) | Individual method to be used and concurrent positive control. Harlan to be asked to assess solubility in 1% Pluronic L92, as well as DMF. NON-SENSITISER
Ames screen | COVANCE | 20. Feb 12 | Draft report received 9/3/2012 | 19. Apr 12 | Requested to be finalised 21-Mar-12 | Negative
GLP Ames | COVANCE | 4 wks from study commencement | w/e 20 April 12 |  | In-life complete. Report being finalised 26/4/12 | Negative
in vitro micronucleus assay in human lympocytes | COVANCE | 6 wks from study commencement | w/e 27 April 2012 |  | In-life complete. Report being finalised 26/4/12 | Negative
hrpt assay - mouse lymphoma cells | COVANCE | 10 wks from study commencement |  |  | Protocol reviewed 24/4. V2 requested for Sponsor review | Laboratory requested to initiate study

## Slide 17
DIAMMINEDICHLOROPALLADIUM: TOXICOLOGY STUDIES |  |  |  |  | 
Study | CRO | Availability of results | Proposed draft report date | Status | Comments
Acute oral toxicity - acute toxic class OECD TG423 | CHARLES RIVER UK | Apr 12 | 15. Jun 12 | In life completed 26 Apr 12 | 2000 mg/kg not tolerated
Preliminary to combined oral repeat dose toxicity with reproduction/development toxicity screening test | CHARLES RIVER UK | 07. Mai 12 | 16. Jul 12 | In life | Study started with 2 dose levels, third to be confirmed depending on results
Combined oral repeat dose toxicity with reproduction/development toxicity screening test OECD TG422 | CHARLES RIVER UK |  | Within 7 months of study commencement |  | Draft protocol requested
Development of methodologies for the formulation analysis of palladium in oral gavage formulations | CHARLES RIVER UK | Jan 12 | No formal report | Completed 10 Feb 12 | Acceptable formulation in 0.5% HPMC with good analytical accuracy.
Validation of methodologies for the formulation and analysis of palladium in oral gavage dosing formulations | CHARLES RIVER UK | Feb 12 | Apr 12 | Awaiting draft report | Completed 01-Mar-12. Formulations prepared at 0.1 mg/mL and 200 mg/mL in 0.5% high viscosity HPMC are stable for at least 9 days at 2-8degC in the dark and at ambient laboratory temperature in the dark.

## Slide 18: DDP Acute toxicity
Appropriate route of exposure
  Currently testing oral route
  Reach requires testing second route of exposure if appropriate
DDP
  Enabling test results
    Low dustiness
    < 1% deposition to lung
    Not irritating to skin
    (no bio-elution testing planned)
  Suggest: inhalation route not appropriate
  Dermal exposure: need feedback from members if dermal route is relevant

## Slide 19: Next Steps - Discussion

## Slide 20: Scope – Hydrous vs. anhydrous forms
Substance | Feedback | Conclusion
PdO | Hydrated form not produced, “Hydrated PdO” might be same as Pd(OH)2 Anhyd. not available for testing either | Hydrous form not produced, Not available for testing Prepare dossiers for anhyd. form only

## Slide 21: Sensitisation
Sensitisation data important for future ES work: need to prioritise
Final scope will depend on outcome irritation tests
Selection of testing laboratory for full testing programme
  DDP tested at Harlan
    Test case for full programme
    Not overwhelming
  Potential alternative: CiToxLAB
    Very good experience by RSA
    Not many good labs available for this endpoint
    Cost LLNA: 4435 Euros at LAB vs. 5020 Euros at Harlan (5 animals, individual lymph nodes)
    Suggest to conduct LLNA testing at LAB

## Slide 22: Genotoxicity
Consulted with independent genotoxicity expert (David Kirkland)
  Impact of extreme pH on PGM genotox study results
  (Apparently) conflicting study results on Rh (III) substances
Recommendation
  Deviate from HERAG
    Ames assay can produce false negative results for metals
    But Ames can be used unless there is evidence to the contrary, in particular if positive results are reported/ no cytotoxicity
  Follow ECHA guidance for genotoxicity testing
  Genotoxicity strategy revised accordingly
  Rh(III): next slides

## Slide 23: Rh(III) Genotoxicity
Existing studies
  All studies listed below are valid
  Positive findings for all substances, except Rh trinitrate
  Reason for neg. Rh(NO3)3 results unclear
    Low solubility (=low dose)?
    Speciation changes?
Substance | Genotoxicity endpoint | pH value
CASRN 20765-98-4. Rhodium trichloride “hydrate” | Positive in vitro Ames test | <2
 | Positive in vitro mouse lymphoma assay | 
 | Positive in vitro micronucleus assay | 
 | Positive in vivo micronucleus assay | 
CASRN 10139-58-9. Rhodium trinitrate | Negative in vitro Ames test | 1.3 (hydrate)
 | Negative in vivo micronucleus assay | 
CASRN 42204-14-8. Rhodium (III) acetate | Positive in vitro Ames test | Not known
CASRN 15492-38-3. Rhodium triiodide | Positive in vitro Ames test | 4.2

## Slide 24: Rh(III) Genotoxicity
Suggest to read across positive findings for Rh(III)
  Rh(III) toxic agent
  Recommended by Prof Kirkland
  Recommended by DECOS
Does PGM WG agree?
Potential consequences: next slide

## Slide 25: Rh(III) read across - discussion
Name of the substance |  |  |  | 
 | Ox state | Rh (III) R-A | Comments | 
Rhodium (solid only) | 0 | No | Need to evaluate wrt transformation/dissolution data | 
Carbonyl(pentane-2,4-dionato-O,O')(triphenylphosphine)rhodium (solid only) | 1 | No | Provided, there is no potential for oxidation from I to III. Evidence that there is the potential to transform into this species would again indicate that Muta. Cat 2 may be appropriate. | 
Carbonylhydrotris(triphenylphosphine)rhodium (solid only) | 1 | No | “ | 
Dicarbonyl(pentane-2,4-dionato-O,O')rhodium (solid only) | 1 | No | “ | 
Rhodium tris(2-ethylhexanoate) (in solution) | 3 | Yes? | Muta. Cat 2 | 
Rhodium trichloride (anhydrous) | 3 | yes | Muta. Cat 2 | 
Rhodium trichloride (hydrate) |  |  | Muta. Cat 2 | 
Di-µ-chloro-bis(hapto-1,5-cyclooctadiene)dirhodium(I) (solid only) | 1 | No | Provided, there is no potential for oxidation from I to III. Evidence that there is the potential to transform into this species would again indicate that Muta. Cat 2 may be appropriate. | 
Tris(triphenylphosphine) rhodium (I) chloride (solid only) | 1 | No | Provided, there is no potential for oxidation from I to III. Evidence that there is the potential to transform into this species would again indicate that Muta. Cat 2 may be appropriate. | 
Rhodium triiodide (solid only) | 3 | Yes | Muta. Cat 2 | 
Dirhodium trisulphate | 3 | Yes | Muta. Cat 2 | 
Dirhodium trioxide (solid only) | 3 | Yes? but substance is insoluble so r-a questionable | Need to evaluate wrt transformation/dissolution data | 
Rhodium (III) acetate | 3 | Yes | Muta. Cat 2 | 
Rhodium trinitrate (in solution) | 3 | Yes | Muta. Cat 2 | 
Rhodium trihydroxide (solid only) | 3 | Yes | Muta. Cat 2 | 
Triammonium hexachlororhodate (solid only) | 3 | Need to discuss | Positive Ames test but no in vivo data | 
Diammonium sodium hexakis(nitrito-N)rhodate (solid only) | 3 | Need to discuss | Muta. Cat 2? | 

## Slide 26: Genotoxicity - other
Format of reporting: addendum to ITS
  Suggest to approve
Platinum dinitrate
  Need to proceed to in-vivo testing
  Do in vivo micronucleus first or do directly Comet assay?
Tetraammineplatinum dinitrate
  WCA recommend new Ames assay
  Suggest to read across from Tetraammineplatinum dichloride and –hydrogencarbonate
Diammonium hexachloropalladate
  Existing valid (neg.) Ames test, but with limitations (4 strains)
  Suggest to conduct confirmatory Ames test with 5 strains

## Slide 27: Genotoxicity - other
Selection of testing lab for full testing programme
  Suggest to continue testing with Covance
  Very good experience
  Support by D. Kirkland if necessary

## Slide 28: Ecotox testing - other
Selection of testing lab for full testing programme
  Good experience with Fraunhofer Institute Schmallenberg in DDP testing
  Good experience with Brixham in Gold and PM-CN programme
  Cost: Fraunhofer and Brixham costs comparable, both offer competitive prices
  Suggest to split full testing programme between Fraunhofer and Brixham

## Slide 29: Exposure Scenarios
Heads-up
  ES work will start in June/July 2012
  Your support is needed
Time line
  31st May: coordination meeting EBRC/WCA/PMC
  June/July: PMG WG ES meeting
For discussion at June/July mtg:
  Scope/resources of ES work: conduct whole programme in 2012 or phased approach?
  Need company experts at the meeting

## Slide 30: Next steps - Timeline

## Slide 31: Timeline fast-track - for 2013 deadline

## Slide 32: Timeline full testing programme