## quote
Quote for the study on the effects of soluble silver on the gut bacterial microbiota (10 wk)
Product or task | Description | Provider | unit price | quantity | total price
Animals
Wistar rats | females, 4 weeks, 100-124 g | Janvier | 13.61 | 40 | 544.4
| males, 4 weeks, 100-124 g | Janvier | 13.61 | 40 | 544.4
| delivery boxes | Janvier | 27 | 14 | 378
| transport | Janvier | 125 | 1 | 125
mixing Ag Ac with diet |  | PMC/Carfill | 1000 | 3 | 3000
animal facility | room (price/month) | Animalerie Centrale UCL | 249 | 3 | 747
| entry (price/person/month) | 2 persons | 52 | 6 | 312
| litter | Animalerie Centrale UCL | 34.3 | 6 | 205.8
Consumables | tubes, tips, ... |  |  |  | 2000
Subtotal |  |  |  |  | 7856.6
Analyses
Subtotal | Cf "items" page |  |  |  | 34120 | Of which ICP-MS analyses: € 21.600 (+overhead + VAT: € 30.456)
Personnel
experimental design and data analysis | Sybille van den Brule (month) | UCL | 8000 | 1 | 8000
NGS data analysis | Jérôme Ambroise (month) | UCL | 8000 | 1 | 8000
sample collection, DNA extractions and other assays | technician (month) | UCL | 4000 | 1 | 4000
Animal care and exposure | technician (month) | UCL | 4000 | 3 | 12000
Subtotal |  |  |  |  | 32000
|  |  |  | total | 73976.6
|  |  |  | overhead (20%) | 14795.32
|  |  |  | VAT (21%) | 15535.086
|  |  |  | TOTAL | 104307.006
Optional
Interpretation of microbiota results | Sybille van den Brule (month) | UCL | 8000 | 1 | 8000 | We would like to include this (assuming Ag has effects on the microbiota)
RNA work | technician (month) | UCL | 4000 | 1 | 4000
RNA Seq sample preparation and quality assessment |  | UCL | 50 | *
intestinal tissue transcriptomics (RNA Seq) |  | outsourced | 1000 | *
RNA Seq data analysis | Jérôme Ambroise (month) | UCL | 8000 | 1 | 8000
Interpretation of RNA Seq results | Sybille van den Brule (month) | UCL | 8000 | 1 | 8000 | 28200
* : the samples of interest should be determined post-hoc

## items
| type of analysis | time | n | males | females | unit price | total
animals |  |  | 80 | 40 | 40
cages |  |  | 40 | 20 | 20
body weight |  | At exposure start, 1x/wk along exposure and just before sacrifice = 11 times | 880 | 440 | 440 | 2 | 1760
food consumption |  | 3x/wk/cage to calculate actual AgAc daily intake = 30 times | 1200 | 600 | 600 | 2 | 2400
blood sampling 28 d | blood sampling | At 28d (4 wk) | 80 | 40 | 40 | 2 | 160
Ag-B | ICP-MS | At 28d (4 wk) | 80 | 40 | 40 | 30 | 2400
Se-P | ICP-MS | At 28d (4 wk) | 80 | 40 | 40 | 30 | 2400
Cu-P | ICP-MS | At 28d (4 wk) | 80 | 40 | 40 | 30 | 2400
ferroxidase-P | Cp oxidase activity | At 28d (4 wk) | 80 | 40 | 40 | 12.5 | 1000
Ag feces/cage | ICP-MS | At 28d (4 wk) | 32 | 16 | 16 | 30 | 960
blood sampling 10 wk | blood sampling | At 70d (10 wk) | 80 | 40 | 40 | 2 | 160
Ag-B | ICP-MS | At 70d (10 wk) | 80 | 40 | 40 | 30 | 2400
Se-P | ICP-MS | At 70d (10 wk) | 80 | 40 | 40 | 30 | 2400
Cu-P | ICP-MS | At 70d (10 wk) | 80 | 40 | 40 | 30 | 2400
ovary weight | weight | At 70d (10 wk) | 40 |  | 40 | 3 | 120
uterus weight | weight | At 70d (10 wk) | 40 |  | 40 | 3 | 120
testis weight | weight | At 70d (10 wk) | 40 | 40 |  | 3 | 120
brain weight | weight | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
thymus weight | weight | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
spleen weight | weight | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
liver weight | weight | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
kidney weight | weight | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
ovary Ag | ICP-MS | At 70d (10 wk) | 40 |  | 40 | 30 | 1200
uterus Ag | ICP-MS | At 70d (10 wk) | 40 |  | 40 | 30 | 1200
testis Ag | ICP-MS | At 70d (10 wk) | 40 | 40 |  | 30 | 1200
ovary PFA | storage for histopath | At 70d (10 wk) | 40 |  | 40 | 3 | 120
uterus PFA | storage for histopath | At 70d (10 wk) | 40 |  | 40 | 3 | 120
testis PFA | storage for histopath | At 70d (10 wk) | 40 | 40 |  | 3 | 120
brain PFA | storage for histopath | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
thymus PFA | storage for histopath | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
spleen PFA | storage for histopath | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
liver PFA | storage for histopath | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
kidney PFA | storage for histopath | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
ileum PFA | storage for histopath | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
colon PFA | storage for histopath | At 70d (10 wk) | 80 | 40 | 40 | 3 | 240
ileum mRNA | storage for optional RNA seq later? | At 70d (10 wk) | 80 | 40 | 40 | 5 | 400
colon mRNA | storage for optional RNA seq later? | At 70d (10 wk) | 80 | 40 | 40 | 5 | 400
fecal DNA | DNA extraction | At 70d (10 wk) | 80 | 40 | 40 | 6 | 480
NGS | biome seq | At 70d (10 wk) | 80 | 40 | 40 | 60 | 4800
TOTAL | [6 empty] | 34120
MISSING:
Ag feces/cage | ICP-MS | At 28d (4 wk) | 8 | 4 | 4 | 30 | 240
Ag feces/rat | ICP-MS | At 70d (10 wk) | 80 | 40 | 40 | 30 | 2400
ferroxidase-P | Cp oxidase activity | At 70d (10 wk) | 80 | 40 | 40 | 12.5 | 1000
NEW TOTAL | [6 empty] | 37760
Note on B1: Katrien Arijs: column added by Katrien
Note on C1: Katrien Arijs: column added by Katrien
Note on A12: Katrien Arijs: Analysis at 10 wks missing?
Note on A13: Katrien Arijs: Analysis per rat at 10 wks missing?
Note on D13: Katrien Arijs: Should be 40? Detailed design mentions 2 rats/cage
Note on E13: Katrien Arijs: Should be 20?
Note on F13: Katrien Arijs: Should be 20?

## time schedule
Time schedule
weeks
Test Ag, Cu and Se measurement by ICP-MS
rat acclimation | 2 | June
exposure duration | 10 | July (wk 28-37)
DNA extraction | 1 | Sept (wk 38)
Ceruloplasmin activity | 1 | Sept (wk 38)
Ag, Cu and Se measurement by ICP-MS | 4 | October (wk 40)
mrDNA sequencing | 4 | October (wk 40)
sequencing analysis | 4 | November
overall analysis | 2 | December